## Sheet1
|  | Iteration 0 |  |  | Iteration 1 |  |  | Iteration 2 |  |  | Iteration 3 |  |  | Iteration 4 |  |  | Iteration 5 |  |  | Release 1
ID | Risk Name | Impact | % Prob | Severity | Impact | % Prob | Severity | Impact | % Prob | Severity | Impact | % Prob | Severity | Impact | % Prob | Severity | Impact | % Prob | Severity
1 | Something about forming the dev team | 3 | 50% | 1.5 | 3 | 10% | 0.3 | 3 | 5% | 0.15 | 3 | 0% | 0 | 3 | 0% | 0 | 3 | 0% | 0
2 | Special resources required, not available for purchase. | 2 | 45% | 0.9 | 2 | 45% | 0.9 | 2 | 45% | 0.9 | 2 | 0% | 0 | 2 | 0% | 0 | 2 | 0% | 0
3 | Poor results from customer focus-groups for requirements gathering. | 3 | 45% | 1.35 | 3 | 0% | 0 | 3 | 0% | 0 | 3 | 0% | 0 | 3 | 0% | 0 | 3 | 0% | 0
4 | Extra DB licenses required for purchase. | 2 | 40% | 0.8 | 2 | 40% | 0.8 | 2 | 20% | 0.4 | 2 | 15% | 0.3 | 2 | 0% | 0 | 2 | 0% | 0
5 | legacy system stability problems. | 2 | 25% | 0.5 | 2 | 25% | 0.5 | 2 | 25% | 0.5 | 2 | 25% | 0.5 | 2 | 10% | 0.2 | 2 | 0% | 0
6 | Server upgrade necessary. | 2 | 20% | 0.4 | 2 | 20% | 0.4 | 2 | 20% | 0.4 | 2 | 20% | 0.4 | 2 | 20% | 0.4 | 2 | 20% | 0.4
7 | Access to user community. | 2 | 10% | 0.2 | 2 | 10% | 0.2 | 2 | 10% | 0.2 | 2 | 10% | 0.2 | 2 | 10% | 0.2 | 2 | 10% | 0.2
8 | High team turn-over. | 1 | 10% | 0.1 | 1 | 10% | 0.1 | 1 | 10% | 0.1 | 1 | 10% | 0.1 | 1 | 10% | 0.1 | 1 | 10% | 0.1
9 | Chairs are too uncomfortable. | 3 | 5% | 0.15 | 3 | 5% | 0.15 | 3 | 5% | 0.15 | 3 | 5% | 0.15 | 3 | 5% | 0.15 | 3 | 5% | 0.15
10 | Testers take too much vacation. | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 10% | 0 | 0 | 10% | 0 | 0 | 0% | 0
|  |  |  | 59 |  |  | 33.5 |  |  | 28 |  |  | 16.5 |  |  | 10.5 |  |  | 8.5